## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
sprint 1 | sprint 1 | US_01 | As an OTT user, I want real-time speech recognition from English/Hindi input so that live audio is transcribed accurately with low latency. | MUST HAVE | None |  | 3- Completed
sprint 1 | sprint 1 | US_02 | As a translator, I want to translate recognized text from source languages to 12+ target languages using Azure OpenAI. | MUST HAVE | US_01 |  | 3- Completed
sprint 1 | sprint 1 | US_03 | As an end-user, I want neural text-to-speech synthesis in target languages so that translated content is output as natural-sounding audio. | MUST HAVE | US_02 |  | 3- Completed
sprint 1 | sprint 2 | US_04 | As an OTT integrator, I want an end-to-end speech-to-speech pipeline with streaming support. | MUST HAVE | US_01,US_02,US_03 |  | 3- Completed
sprint 2 | sprint 2 | US_05 | As a developer, I want a FastAPI-based REST API with endpoints for recognition, translation, and full pipeline so that the system can be integrated into external apps. | SHOULD HAVE | US_04 |  | 3- Completed
sprint 2 | sprint 3 | US_06 | As a real-time user, I want WebSocket support for bidirectional streaming translation so that continuous audio is handled efficiently. | SHOULD HAVE | US_05 |  | 3- Completed
sprint 2 | sprint 2 | US_07 | As an admin, I want configuration management via .env and settings.py so that deployment is flexible across environments. | SHOULD HAVE | None |  | 3- Completed
sprint 3 | sprint 4 | US_08 | As a quality assurer, I want evaluation metrics (BLEU, WER, latency) so that performance can be measured and optimized. | COULD HAVE | US_01 |  | 2- In Progress
sprint 3 | Not started | US_09 | As an OTT developer, I want an adapter for multi-device stream delivery with quality monitoring so that it works seamlessly with platforms. | COULD HAVE | US_02 |  | 2- In Progress
sprint 4 | Not started | US_10 | As a user, I want support for additional languages beyond the initial 14 so that global coverage expands. | COULD HAVE | US_04 |  | 1- Not Started
sprint 4 | sprint 3 | US_11 | As a deployer, I want Redis queuing, async processing, and load balancing so that the system handles high-throughput scenarios. | COULD HAVE | US_05 |  | 2- In Progress
sprint 5 | sprint 3 | US_12 | As a tester, I want example scripts for unit and integration testing so that reliability is ensured. | SHOULD HAVE | US_05 |  | 3- Completed
sprint 5 | Not started | US_13 | As a maintainer, I want HTTPS, rate limiting, and input validation so that the API is protected from abuse. | SHOULD HAVE | US_05 |  | 3- Completed
sprint 6 | Not started | US_14 | As an advanced user, I want custom voice training for TTS so that branded voices can be used. | WON'T HAVE | US_03 |  | 1- Not Started
sprint 6 | Not started | US_15 | As a mobile user, I want an offline-capable SDK so that translation works without internet. | WON'T HAVE | US_04 |  | 1- Not Started
Sprint 7 | Not started | US_16 | As an ops team, I want Kubernetes deployment and monitoring dashboard so that production is streamlined. | WON'T HAVE | US_11 |  | 1- Not Started
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Whisper model not installing correctly on local machine | Installed CUDA, fixed PyTorch version mismatch
Sprint 1 | Day 2 | Microphone input stream not recognized | Configured PyAudio + tested with sample WAV
Sprint 1 | Day 3 | Background noise causing incorrect recognition | Added noise reduction + VAD preprocessing
Sprint 1 | Day 4 | Hindi speech accuracy low | Adjusted sampling rate + added custom Hindi dataset
Sprint 1 | Day 5 | Output delays in real-time conversion | Enabled faster Whisper model (“small” version)
Sprint 2 | Day 1 | Live commentary audio not recorded properly | Switched to 16kHz mono recording
Sprint 2 | Day 2 | Need more clean English/Hindi samples | Collected dataset from open commentary sources
Sprint 2 | Day 3 | Large audio files slowing pipeline | Chunked audio into 5-second segments
Sprint 2 | Day 4 | Feature extraction taking long time | Optimized MFCC extraction with parallel processing
Sprint 2 | Day 5 | Data cleaning scripts failing | Fixed file path issues + automated preprocessing
Sprint 3 | Day 1 | Google Translate API rate limits exceeded | Added caching & retry mechanism
Sprint 3 | Day 2 | Azure OpenAI translations inconsistent | Fine-tuned prompt & used deterministic temperature
Sprint 3 | Day 3 | BLEU score low for certain languages | Applied domain-specific translation examples
Sprint 3 | Day 4 | Slow translation for high-volume text | Enabled streaming translation
Sprint 3 | Day 5 | Multi-language handling errors | Standardized languagecodes (en, hi, ta, te, etc.)
Sprint 4 | Day 1 | Training model too slow | Switched to smaller architecture & GPU batch training
Sprint 4 | Day 2 | Loss not decreasing | Tuned learning rate & optimizer
Sprint 4 | Day 3 | Overfitting problems | Applied regularization & dropout
Sprint 4 | Day 4 | Inaccurate translations for long sentences | Added context-preserving translation chunks
Sprint 4 | Day 5 | Latency still high | Compressed model + optimized inference
Sprint 5 | Day 1 | Pipeline not syncing (speech → text → translate → speech) | Adjusted buffer size
Sprint 5 | Day 2 | gTTS output too robotic | Switched to Azure Neural TTS
Sprint 5 | Day 3 | Audio output delayed | Used multiprocessing
Sprint 5 | Day 4 | Flask API unable to handle continuous streaming | Added WebSockets
Sprint 5 | Day 5 | Ngrok disconnecting during demo | Switched to persistent tunnel
Sprint 6 | Day 1 | OTT video not syncing with translated audio | Implemented timestamp alignment
Sprint 6 | Day 2 | Audio overwriting original feed | Enabled dual-track audio
Sprint 6 | Day 3 | Web player compatibility issues | Standardized audio encoding to AAC
Sprint 6 | Day 4 | Translated audio too fast/slow | Added dynamic time-stretching logic
Sprint 6 | Day 5 | API endpoint returning CORS error | Enabled CORS in backend
Sprint 7 | Day 1 | Docker container missing FFmpeg | Installed FFmpeg in Dockerfile
Sprint 7 | Day 2 | Deployment failing on Azure | Updated environment variables
Sprint 7 | Day 3 | High memory usage | Enabled model loading on-demand
Sprint 7 | Day 4 | Load balancer not routing audio streams | Added sticky sessions
Sprint 7 | Day 5 | Mobile device playback issues | Adjusted output bitrate
Sprint 8 | Day 1 | Multi-language switching lag | Cached top 12 languages
Sprint 8 | Day 2 | UI not showing translated output live | Fixed frontend WebSocket event
Sprint 8 | Day 3 | Demo crashes due to long audio | Added chunk-based processing
Sprint 8 | Day 4 | QA team found mismatched timestamps | Fixed with improved sync logic
Sprint 8 | Day 5 | Final video feed slightly out of sync | Applied final latency adjustments

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-26 | 2025-10-03 | Frontend | 2025-09-26 | 2025-10-05 |  | Developed Html
2 | Sprint 2 | 2025-10-03 | 2025-10-10 | Frontend | 2025-10-03 | 2025-10-11 |  | Developed CSS
3 | Sprint 3 | 2025-10-10 | 2025-10-17 | Frontend | 2025-10-10 | 2025-10-18 |  | Developed Js
4 | Sprint 4 | 2025-10-17 | 2025-10-24 | Frontend | 2025-10-17 | 2025-10-24 |  | Developed Python
5 | Sprint 5 | 2025-10-24 | 2025-10-31 | Backend | 2025-10-24 | 2025-11-02 |  | Taking Dataset
6 | Sprint 6 | 2025-10-31 | 2025-11-07 | Backend | 2025-10-31 | 2025-11-08 |  | Training Model
7 | Sprint 7 | 2025-11-07 | 2025-11-10 | Backend | 2025-11-07 | 2025-11-10 |  | Speech to text & text to speech work